

# Lessard-Sams Outdoor Heritage Council Prairie Chicken Habitat Partnership of the Southern Red River Valley - Phase XII ML 2026 Request for Funding

## General Information

**Date:** 06/26/2025

**Proposal Title:** Prairie Chicken Habitat Partnership of the Southern Red River Valley - Phase XII

**Funds Requested:** $12,004,600

**Confirmed Leverage Funds:** -

**Is this proposal Scalable?:** Yes

### Manager Information

**Manager's Name:** Sabin Adams **Title:** MN State Coordinator **Organization:** Pheasants Forever **Address:** 1783 Buerkle Circle  **City:** St. Paul, MN 55110 **Email:** sadams@pheasantsforever.org **Office Number:** 320-250-6317 **Mobile Number:** 3202506317 **Fax Number:**   **Website:** www.pheasantsforever.org

### Location Information

**County Location(s):** Clay and Otter Tail.

**Eco regions in which work will take place:**

Forest / Prairie Transition

Prairie

**Activity types:**

Protect in Fee

Restore

**Priority resources addressed by activity:**

Prairie

## Narrative

### Abstract

The Minnesota Prairie Chicken Society in partnership with Pheasants Forever seek to protect and restore parcels within the Minnesota prairie chicken range. Focus will be on parcels that will specifically benefit prairie chickens, a species of special concern. Acquisitions will be located in the prairie or prairie/forest planning regions with an emphasis in the primary prairie chicken range. Parcels will be transferred to either the MN DNR as WMA’s or the USFWS as WPA’s and will be open to the public.

### Design and Scope of Work

Greater prairie chickens are a grassland dependent species found largely in the beach ridges of Glacial Lake Agassiz in western Minnesota. Grassland complexes composed of various successional stages (i.e. age of habitat resulting in changing plant community), and at least 320 acres in size are required by this species. Loss of Conservation Reserve Program (CRP) acres and conversion from grassland to row crop agriculture are the two major factors reducing quality or the habitat available to prairie chickens. As a charismatic upland gamebird, prairie chickens serve as flagship or ambassador for other grassland dependent species. Protection and restoration of habitat for the benefit of prairie chickens will, in turn, positively benefit other species such as the chestnut-collared longspur and Dakota Skipper (both species listed by the MN DNR as endangered).   
  
The focus of this partnership is to permanently protect native and restored prairies and associated wetland habitats to both increase and stabilize prairie chicken populations in western Minnesota. This is done by focusing on remnant prairies within core and corridor areas of the Minnesota Prairie Conservation Plan (MNPCP). Proposed tracts, with willing sellers who value wildlife habitat, are ranked based on the following criteria: 1) distance to the nearest prairie chicken lek, 2) location in or outside of a core area from the Minnesota Prairie Conservation Plan (MPCP), 3) distance to the nearest public hunting land (WPA or WMA), 4) tract size, 5) current grassland type (native prairie, restored prairie, brome, or row crop), and 6) wetland density and predicted waterfowl breeding pairs (wetlands can provide important habitat for prairie chickens over their annual life cycle). Purchased tracts will be restored and/or enhanced to their fullest potential using grant funds. When appropriate, tracts will be transferred to the MN DNR as Wildlife Management Areas (WMA) or to the USFWS as Waterfowl Production Areas (WPA) and will be responsible for future management.   
  
This proposal delivers numerous stateside conservation plan goals by protecting, restoring, and enhancing grasslands and wetlands in strategic areas. The MPCP specifically states that an ecosystem measure of success is stable or growing prairie chicken populations in Minnesota. The MPCP is ideally suited for greater prairie chicken management with core areas containing large contiguous blocks of grassland and smaller grassland patches serving as corridors allowing birds to maintain populations outside the core areas as well as move across the landscape. Additional benefits of this work is protection and restoration of the extensive wetland systems encompassed by these tracts. Water storage sequestering and storing carbon, water quality, diversity of flora and fauna, and reducing erosion are among the many benefits of fully functional wetland systems.

### Explain how the proposal addresses habitat protection, restoration, and/or enhancement for fish, game & wildlife, including threatened or endangered species conservation

PF actively engages in conservation priority discussions with state and government agencies, to determine what areas are the highest priority for adding permanently protected lands in the prairie, prairie/forest transition, and metro planning areas. High priority is given to parcels whose restoration and protection benefit rare, threatened, & endangered species. Often the only locations where many threatened and endangered species are found is on existing habitat complexes. This proposal builds upon those complexes allowing for expansion and increased populations of those species.  
  
When selecting projects for this proposal, PF uses the latest GIS data and works with DNR and USFWS staff to identify locations that benefit species of greatest conservation need. Additionally, species of greatest conservation need are considered and can influence restoration plans after the land is permanently protected. By increasing the amount, functionality, and productivity of grassland landscapes for these species, we aim to slow population decline.

### What are the elements of this proposal that are critical from a timing perspective?

Prairie chickens exhibit high sight fidelity, returning to the same leks (booming grounds) in the spring to perform courtship displays and nesting in the same areas on an annual basis. This characteristic makes prairie chickens extremely sensitive to habitat loss. The ability to purchase critical tracts as they become available is imperative to the success of this species as it is more difficult to establish breeding areas than it is to maintain them.

### Describe how the proposal expands habitat corridors or complexes and/or addresses habitat fragmentation:

As this proposal is fully integrated into the Minnesota Prairie Conservation Plan (MPCP), its focus is on acquisition and restoration in and around core habitat and corridors. Selection of tracts include proximity to known prairie chicken habitat, leks, and presence of other rare features identified by the MN County Biological Survey. Presence of prairie chickens are highly correlated with large expanses of grassland, which are most often large complexes made up of WMA's and WPA's. For this reason, many of the tracts selected build on these large complexes. In protecting and restoring large portions of habitat, we reduce both habitat fragmentation and reduce the cost of future management.

### Which top 2 Conservation Plans referenced in MS97A.056, subd. 3a are most applicable to this project?

Grassland Conservation Plan for Prairie Grouse

Minnesota Prairie Conservation Plan

### Explain how this proposal will uniquely address habitat resilience to climate change and its anticipated effects on game, fish & wildlife species utilizing the protected or restored/enhanced habitat this proposal targets.

Healthy ecosystems with diverse native plant communities and fully functional hydrologic systems are more resilient to the changing climate. Native plant communities not only convert CO2, but also outcompete invasive species that reduce the tracts value to wildlife. Restored or enhanced wetlands optimize groundwater recharge, nitrogen and carbon cycling, and constantly provide water for local game, fish, and wildlife species. By protecting, restoring, and enhancing targeted tracts we're creating habitats that are both resilient to climate change and require less maintenance due to their self-regulating nature.

### Which LSOHC section priorities are addressed in this proposal?

**Forest / Prairie Transition**

Protect, restore, and enhance habitat for waterfowl, upland birds, and species of greatest conservation need

**Prairie**

Protect, enhance, or restore existing wetland/upland complexes, or convert agricultural lands to new wetland/upland habitat complexes

### Describe how this project/program will produce and demonstrate a significant and permanent conservation legacy and/or outcomes for fish, game, and wildlife, and if not permanent outcomes, why it is important to undertake at this time:

This partnership protects and restores parcels that become a permanent part of the grassland habitat base for many species of wildlife. All lands protected will be restored and transferred to the MN DNR as a Wildlife Management Area (WMA), or to the U.S. Fish and Wildlife Service as a Waterfowl Production Area (WPA). These agencies will provide the long-term management required to maintain the biological productivity of these lands.

## Outcomes

### Programs in forest-prairie transition region:

Protected, restored, and enhanced nesting and migratory habitat for waterfowl, upland birds, and species of greatest conservation need ~ *Strategic parcels that increase the functionality of existing habitat will be acquired and restored to functioning wetlands with diverse upland prairie to serve as habitat for pollinators, resident and migratory game and non game species. Lands will be protected to provide accelerated wildlife habitat and public access, monitored by Minnesota DNR of United States FWS. Protected and restored acres will be measured against goals outlined in the "Minnesota's Wildlife Management Area Acquisition - The Next 50 Years" and "Minnesota Prairie Conservation Plan".*

### Programs in prairie region:

Key core parcels are protected for fish, game and other wildlife ~ *Strategic parcels that increase the functionality of existing habitat will be acquired and restored to functioning wetlands with diverse upland prairie to serve as habitat for pollinators, resident and migratory game and non game species. Lands will be protected to provide accelerated wildlife habitat and public access, monitored by Minnesota DNR of United States FWS. Protected and restored acres will be measured against goals outlined in the "Minnesota's Wildlife Management Area Acquisition - The Next 50 Years" and "Minnesota Prairie Conservation Plan".*

### What other dedicated funds may collaborate with or contribute to this proposal?

N/A

### Per MS 97A.056, Subd. 24, Please explain whether the request is supplanting or is a substitution for any previous funding that was not from a legacy fund and was used for the same purpose.

This proposal supplements past investments and is aimed at accelerating the protection and restoration of strategic parcels.

### How will you sustain and/or maintain this work after the Outdoor Heritage Funds are expended?

All lands will be enrolled into the WMA or WPA system and will be managed in perpetuity by the MNDNR or USFWS, respectively. All acquisitions will be restored and/or enhanced to as high quality as practicable, with the knowledge that quality and comprehensive restorations utilizing native species result in lower management costs. In addition, local PF chapter members and volunteers maintain significant interest in seeing the habitat and productivity of acquired parcels are high. MPCS, PF, MNDNR and USFWS will develop an ecological restoration and management plan for each parcel. Grant and partner dollars will be used for the initial site development and restoration/enhancement work.

### Actions to Maintain Project Outcomes

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Year** | **Source of Funds** | **Step 1** | **Step 2** | **Step 3** |
| Post Transfer | State of MN/Federal | Monitoring | Maintainance | Habitat Management |

### Provide an assessment of how your program may celebrate cultural diversity or reach diverse communities in Minnesota, including reaching low- and moderate-income households:

The goal of this program is to protect and restore wildlife habitat and make these areas accessible to all Minnesotans, regardless of cultural background or fiscal standing. Properties acquired under this program will be free and open to access by all. These properties can be recreated on by all levels of income from free hiking/wildlife watching to expensive hunting practices. Some acquisitions will be nearby areas with diverse or low-income communities. This program engages with everyone who wants to participate in public lands and the outdoors.

## Activity Details

### Requirements

**Will county board or other local government approval be formally sought\*\* prior to acquisition, per 97A.056 subd 13(j)?**No

**Describe any measures to inform local governments of land acquisition under their jurisdiction:**At minimum, we will notify local government in writing of the intent to acquire and donate lands to the  
state and follow up with questions prior to the acquisition. In cases where there is interest, we will also  
indicate our willingness to attend or ask to attend county or township meetings to communicate our  
interest in the projects and seek support.

**Is the land you plan to acquire (fee title) free of any other permanent protection?**No

**Describe the permanent protection and justification for additional protection:**Because we are working within priority habitat areas, it is possible that parcels could have perpetual  
easements on a portion of them. If a parcel has a perpetual easement and is deemed a high priority by the  
partners, we will follow guidance established by the Outdoor Heritage Fund to proceed, or use non-state  
funding to acquire the protected portion of the property.

**Will restoration and enhancement work follow best management practices including MS 84.973 Pollinator Habitat Program?**Yes

**Is the restoration and enhancement activity on permanently protected land per 97A.056, Subd 13(f), tribal lands, and/or public waters per MS 103G.005, Subd. 15 or on lands to be acquired in this program?**Yes

**Where does the activity take place?**

WMA

WPA

Refuge Lands

### Land Use

**Will there be planting of any crop on OHF land purchased or restored in this program, either by the proposer or the end owner of the property, outside of the initial restoration of the land?**Yes

**Explain what will be planted and include the maximum percentage of any acquired parcel that would be planted into foodplots by the proposer or the end owner of the property:**This proposal may include initial development plans or restoration plans to utilize farming to prepare previously farmed sites for native plant seeding. This is a standard practice across the Midwest to prepare the seedbed for native seed planting. In these restorations, PF's policy is to use non neonicotinoid treated seed and no herbicides other than glyphosate. On a small percentage of WMAs (less than 2.5%), DNR uses farming to provide a winter food source for a variety of wildlife species in agriculture dominated landscapes largely devoid of winter food sources. There are no immediate plans to use farming for winter food on any of the parcels in this proposal.

**Will insecticides or fungicides (including neonicotinoid and fungicide treated seed) be used within any activities of this proposal either in the process of restoration or use as food plots?**No

**Is this land currently open for hunting and fishing?**No

**Will the land be open for hunting and fishing after completion?**Yes

**Describe any variation from the State of Minnesota regulations:**No variation from State of MN regulations for WMA acquisitions. All WPA acquisitions will be open to the public taking of fish and game during the open season according to the National Wildlife Refuge System Improvement Act, United States Code, title 16, section 668dd, et seq.

**Who will eventually own the fee title land?**

State of MN

Federal

**Land acquired in fee will be designated as a:**

WMA

WPA

**Are there currently trails or roads on any of the proposed acquisitions?**No

**Will new trails or roads be developed or improved as a result of the OHF acquisition?**No

**Will the land that you acquire (fee or easement) be restored or enhanced within this proposal's funding and availability?**Yes

### Other OHF Appropriation Awards

**Have you received OHF dollars through LSOHC in the past?**Yes

**Are any of these past appropriations still OPEN?**Yes

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Approp Year** | **Funding Amount Received** | **Amount Spent to Date** | **Funding Remaining** | **% Spent to Date** |
| 2025 | $3,690,000 | - | - | - |
| 2024 | $3,794,000 | $149,749 | $3,644,251 | 3.95% |
| 2023 | $4,400,000 | $3,581,509 | $818,491 | 81.4% |
| 2022 | $4,440,000 | $3,733,883 | $706,117 | 84.1% |
| 2021 | $2,264,000 | $1,987,043 | $276,957 | 87.77% |
| Totals | $18,588,000 | $9,452,184 | $9,135,816 | 50.85% |

## Timeline

|  |  |
| --- | --- |
| **Activity Name** | **Estimated Completion Date** |
| Identify priority acquisitions | 7/1/2026 |
| Contract appraisals ordered | 9/1/2026 |
| Purchase agreements | 2/1/2027 |
| Re-evaluate tract priorities | 2/15/2027 |
| Contract appraisals ordered | 4/1/2027 |
| Purchase agreements | 9/1/2027 |
| Close | 1/1/2030 |
| Restoration complete | 6/30/2030 |

## Budget

### Totals

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Item** | **Funding Request** | **Total Leverage** | **Leverage Source** | **Total** |
| Personnel | $341,300 | - | - | $341,300 |
| Contracts | $2,352,000 | - | - | $2,352,000 |
| Fee Acquisition w/ PILT | $4,042,500 | - | - | $4,042,500 |
| Fee Acquisition w/o PILT | $4,042,500 | $750,000 | PF, Local and Federal | $4,792,500 |
| Easement Acquisition | - | - | - | - |
| Easement Stewardship | - | - | - | - |
| Travel | $3,000 | - | - | $3,000 |
| Professional Services | $240,000 | - | - | $240,000 |
| Direct Support Services | $247,000 | $25,000 | PF | $272,000 |
| DNR Land Acquisition Costs | $97,000 | - | - | $97,000 |
| Capital Equipment | - | - | - | - |
| Other Equipment/Tools | - | - | - | - |
| Supplies/Materials | $495,000 | - | - | $495,000 |
| DNR IDP | $144,300 | - | - | $144,300 |
| **Grand Total** | **$12,004,600** | **$775,000** | **-** | **$12,779,600** |

### Personnel

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Position** | **Annual FTE** | **Years Working** | **Funding Request** | **Total Leverage** | **Leverage Source** | **Total** |
| PF Field Staff | 0.61 | 5.0 | $292,500 | - | - | $292,500 |
| PF Grant Staff | 0.1 | 5.0 | $48,800 | - | - | $48,800 |

**Amount of Request:** $12,004,600 **Amount of Leverage:** $775,000 **Leverage as a percent of the Request:** 6.46% **DSS + Personnel:** $588,300 **As a % of the total request:** 4.9% **Easement Stewardship:** - **As a % of the Easement Acquisition:** -

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Total Leverage (from above)** | **Amount Confirmed** | **% of Total Leverage** | **Amount Anticipated** | **% of Total Leverage** |
| $775,000 | - | 0.0% | $775,000 | 100.0% |

**Detail leverage sources and confirmation of funds:**Leverage is expected from multiple sources including but not limited to federal sources, land value donations, contractor donations and PF. Not every source is 100% confirmed at this point. However, PF has an exemplary track record of delivery and over-achievement of match commitments that further stretch OHF funding.

**Does this proposal have the ability to be scalable?**Yes

### If the project received 50% of the requested funding

**Describe how the scaling would affect acres/activities and if not proportionately reduced, why?**If this project is reduced by 50% we would scale down all acres/activities and dollar amounts  
proportionately.

**Describe how personnel and DSS expenses would be adjusted and if not proportionately reduced, why?**Personnel and DSS will be scaled down proportionately.

### If the project received 30% of the requested funding

**Describe how the scaling would affect acres/activities and if not proportionately reduced, why?**If this project is reduced by 70% we would scale down all acres/activities and dollar amounts  
proportionately.

**Describe how personnel and DSS expenses would be adjusted and if not proportionately reduced, why?**Personnel and DSS will be scaled down proportionately.

### Personnel

**Has funding for these positions been requested in the past?**Yes

**Please explain the overlap of past and future staffing and position levels previously received and how that is coordinated over multiple years?**In general PF staffing is existing and only partially funded by OHF and specifically this request. Billing to any appropriation would only be for time spent on direct and necessary costs incurred as outlined in an Accomplishment Plan.

### Contracts

**What is included in the contracts line?**We anticipate that all of the contract funding will be used for restoration, enhancement, and initial development of the protected acres and $42,000 for adjacent protected lands. This could include but is not limited to wetland/grassland restoration, tree removal, prescribed fire, building removal, posts, signs, and other development

### Professional Services

**What is included in the Professional Services line?**

Appraisals

Other : Acquisition Contractors hired by PF to obtain necessary documentation.

Surveys

Title Insurance and Legal Fees

### Fee Acquisition

**What is the anticipated number of fee title acquisition transactions?**With the proposed budget, we anticipate approximately 7 fee title acquisition transactions

### Travel

**Does the amount in the travel line include equipment/vehicle rental?**No

**Explain the amount in the travel line outside of traditional travel costs of mileage, food, and lodging**NA

**I understand and agree that lodging, meals, and mileage must comply with the current MMB Commissioner Plan:**Yes

### Direct Support Services

**How did you determine which portions of the Direct Support Services of your shared support services is direct to this program?**PF utilizes the Total Modified Direct Cost method. This methodology is annually approved by the U.S. Department of Interior’s National Business Center as the basis for the organization’s Indirect Cost Rate agreement. PF’s allowable direct support services cost is 15%. In this proposal, PF has discounted its rate to 7% of the sum of personnel, contracts, professional services, and   
 travel. We are donating the difference in-kind.

## Federal Funds

**Do you anticipate federal funds as a match for this program?**Yes

**Are the funds confirmed?**No

**What is the approximate date you anticipate receiving confirmation of the federal funds?**7/1/2028

## Output Tables

### Acres by Resource Type (Table 1)

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Type** | **Wetland** | **Prairie** | **Forest** | **Habitat** | **Total Acres** |
| Restore | 0 | 30 | 0 | 0 | 30 |
| Protect in Fee with State PILT Liability | 0 | 825 | 0 | 0 | 825 |
| Protect in Fee w/o State PILT Liability | 0 | 825 | 0 | 0 | 825 |
| Protect in Easement | 0 | 0 | 0 | 0 | 0 |
| Enhance | 0 | 0 | 0 | 0 | 0 |
| **Total** | **0** | **1,680** | **0** | **0** | **1,680** |

### Restoration/Enhancement Acres of OHF Acquired Lands (Table 1a.1)

|  | **RESTORE** |  | **Total** | **ENHANCE** |  | **Total** |
| --- | --- | --- | --- | --- | --- | --- |
|  | **Lands acquired in this proposal** | **Lands acquired with previous OHF approprations (<5yrs old)** |  | **Lands acquired in this proposal** | **Lands acquired with previous OHF approprations (<5yrs old)** |  |
| Protect in Fee with State PILT Liability | 825 | - | 825 | - | - | 0 |
| Protect in Fee w/o State PILT Liability | 825 | - | 825 | - | - | 0 |
| Protect in Easement | - | - | - | - | - | - |
| **Total** | **1,650** | **-** | **1,650** | **-** | **-** | **-** |

### Restoration/Enhancement Acres Breakdown of Existing Protected Lands (Table 1a.2)

|  | **RESTORE** |  | **ENHANCE** |  |
| --- | --- | --- | --- | --- |
|  | **Lands acquired with OHF** | **Lands NOT acquired with OHF** | **Lands acquired with OHF** | **Lands NOT acquired with OHF** |
| DNR Lands (WMA, State Forests, etc) | - | - | 30 | - |
| Non-DNR Lands (city, state, federal, etc.) | - | - | - | - |
| Easements | - | - | - | - |
| **Total** | **-** | **-** | **30** | **-** |

### Total Requested Funding by Resource Type (Table 2)

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Type** | **Wetland** | **Prairie** | **Forest** | **Habitat** | **Total Funding** |
| Restore | - | $42,000 | - | - | $42,000 |
| Protect in Fee with State PILT Liability | - | $5,981,300 | - | - | $5,981,300 |
| Protect in Fee w/o State PILT Liability | - | $5,981,300 | - | - | $5,981,300 |
| Protect in Easement | - | - | - | - | - |
| Enhance | - | - | - | - | - |
| **Total** | **-** | **$12,004,600** | **-** | **-** | **$12,004,600** |

### Acres within each Ecological Section (Table 3)

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Type** | **Metro/Urban** | **Forest/Prairie** | **SE Forest** | **Prairie** | **N. Forest** | **Total Acres** |
| Restore | 0 | - | 0 | 30 | 0 | 30 |
| Protect in Fee with State PILT Liability | 0 | 83 | 0 | 742 | 0 | 825 |
| Protect in Fee w/o State PILT Liability | 0 | 83 | 0 | 742 | 0 | 825 |
| Protect in Easement | 0 | 0 | 0 | 0 | 0 | 0 |
| Enhance | 0 | 0 | 0 | 0 | 0 | 0 |
| **Total** | **0** | **166** | **0** | **1,514** | **0** | **1,680** |

### Total Requested Funding within each Ecological Section (Table 4)

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Type** | **Metro/Urban** | **Forest/Prairie** | **SE Forest** | **Prairie** | **N. Forest** | **Total Funding** |
| Restore | - | - | - | $42,000 | - | $42,000 |
| Protect in Fee with State PILT Liability | - | $598,100 | - | $5,383,200 | - | $5,981,300 |
| Protect in Fee w/o State PILT Liability | - | $598,100 | - | $5,383,200 | - | $5,981,300 |
| Protect in Easement | - | - | - | - | - | - |
| Enhance | - | - | - | - | - | - |
| **Total** | **-** | **$1,196,200** | **-** | **$10,808,400** | **-** | **$12,004,600** |

### Average Cost per Acre by Resource Type (Table 5)

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Type** | **Wetland** | **Prairie** | **Forest** | **Habitat** |
| Restore | - | $1,400 | - | - |
| Protect in Fee with State PILT Liability | - | $7,250 | - | - |
| Protect in Fee w/o State PILT Liability | - | $7,250 | - | - |
| Protect in Easement | - | - | - | - |
| Enhance | - | - | - | - |

### Average Cost per Acre by Ecological Section (Table 6)

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Type** | **Metro/Urban** | **Forest/Prairie** | **SE Forest** | **Prairie** | **N. Forest** |
| Restore | - | - | - | $1,400 | - |
| Protect in Fee with State PILT Liability | - | $7,206 | - | $7,254 | - |
| Protect in Fee w/o State PILT Liability | - | $7,206 | - | $7,254 | - |
| Protect in Easement | - | - | - | - | - |
| Enhance | - | - | - | - | - |

### Target Lake/Stream/River Feet or Miles

## Parcels

**Sign-up Criteria?**No

**Explain the process used to identify, prioritize, and select the parcels on your list:**Parcels are identified and strategically prioritized using the best science and decision support tools (e.g. Prairie Conservation Plan Maps) available. Preference is given to project sites that both help deliver the goals of other recognized conservation initiatives and that build habitat in critical prairie chicken areas. Data layers (i.e. MN Biological Survey, Natural Heritage Database, MN Wildlife Action Plan, Wellhead Protection Areas, Pheasant Action Plan, existing protected land, etc.) are used to help justify projects and focus areas as well as to inform decisions on top priorities for protection and restoration efforts.

### Protect Parcels

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Name** | **County** | **TRDS** | **Acres** | **Est Cost** | **Existing Protection** |
| Doran Lake WPA Addn | Clay | 13945225 | 88 | $425,000 | No |
| Doran Lake WPA Addn | Clay | 13944230 | 73 | $270,100 | No |
| Flickertail Prairie WPA Addn | Clay | 14245234 | 300 | $1,500,000 | No |
| Pelican Valley WPA Addn | Otter Tail | 13643232 | 144 | $1,036,800 | No |
| Ridgeway WPA Addn | Otter Tail | 13244208 | 313 | $2,347,500 | No |

## Parcel Map



